## GlobalSight 8.5.2_20140128
| GlobalSight Smoke Testing |  |  |  |  | Pass
Fail
CHECK | Description | Selenium testcase | Tester | Result | Comments | N/A
User: SuperAdmin
CHECK 01 | Sign in with superAdmin and create a new company. Verify the company can be created. | CreateCompany | Julie Bu | Pass
CHECK 02 | Go to Setup->Users. Verify three users for the company are avalable.The first one is <company>admin, the second is <company>anyone and the last is gs<company>pm. | CreateCompany | Julie Bu | Pass
CHECK 03 | Create a super localization participant. CHECK 03.01 - Verify the super localization participant could be created and edited. CHECK 03.02 - Verify Default Roles feature works. | CreateSuperUsers | Julie Bu | Pass
User: CompanyAdmin or PM
CHECK 04 | Sign in with the <company>admin, <company>anyone and gs<company>pm. CHECK 04.01 - Verify the Globalsight can be accessed. CHECK 04.02 - Verify all items in Home page display correctly. | CreateCompany | Julie Bu | Pass
CHECK 05 | Sign in as the <company>admin. Create serveral new Locale Pairs. Verify Locale Pairs can be created. | CreateLocalePairs | Julie Bu | Pass
CHECK 06 | Create local attribute and super attributes, Verify the attributes can be created and edited. | CreateAttribute | Julie Bu | Pass
CHECK 07 | Create local Attribute Groups, Verify Attribute Groups can be created and edited. | CreateAttributeGroup | Julie Bu | Pass
CHECK 08 | Create Automatic Actions configuration. Verify the Automatic Actions can be created and edited. | CreateAutomaticActions | Julie Bu | Pass
CHECK 09 | Create GS Editions configuration. Verify the GS Edition configuration can be created and edited. | No testcase | Julie Bu
CHECK 10 | Create GS Edition Actions. Verify the GS Edition Action can be created and edited. | No testcase | Julie Bu
CHECK 11 | Create three new Activity Types whose Type is Translate, Review (Editable), Review Only, Automatic Action or GS Edition Action. Verify the new Acticity Types can be created and edited. | CreateActivityType | Julie Bu | Pass
CHECK 12 | Create serveral new Currency. Verify Currency can be created and edited. | CreateCurrency | Julie Bu | Pass
CHECK 13 | Create four Rates whose Rate Type is Fixed, Hourly, Page, Word Count or Word Count by %.Verify the new Rates can be created and edited. | CreateRates | Julie Bu | Pass
CHECK 14 | Change the Permission Groups of admin. Re-log in and verify the changes take affect. | ChangePermissionGroups | Julie Bu | Pass
CHECK 15 | Create serveral Users with Rates who were created in CHECK 13. Log in with new created Users. Verify the Users work and are editable. | CreateUsers | Julie Bu | Pass
CHECK 16 | Create sereral Translation Memories and import TM files into them. Verify Translation Memories can be created and used in the jobs. | CreateTM | Julie Bu | Pass
CHECK 17 | Create several TM Profiles using Translation Memories in CHECK 16. Verify TM Profiles can be created and edited. | CreateTMProfile | Julie Bu | Pass
CHECK 18 | Create four Termbases and import Terminology files whose format is XML,Excel, CSV or TBX. Verify Termbases can be created. | Terminology | Julie Bu | Pass
CHECK 19 | Creae new Projects. Verify Projects can be created and edited. | CreateProject | Julie Bu | Pass
CHECK 20 | Create new Workflows using Projects in CHECK 19, Locale Pairs in CHECK 05, Users in CHECK 15 and Rates in CHECK 13. Verfiy Workflows can be created and edited. | Workflow | Julie Bu | Pass
CHECK 21 | Create new Localization Profiles using Translation Memory Profiles in CHECK 17, Projects in CHECK 19, Workflows in CHECK 20. Verfiy Localization Profiles can be created and edited. | CreateLocalizationProfile | Julie Bu | Pass
CHECK 22 | Create new xml rules. Verify the xml rule can be edited and validated. | CreateXMLRule | Julie Bu | Pass
CHECK 23 | Create new xml DTD. Verify the new xml dtd files can be added/removed. | TestXMLDTD | Julie Bu | Pass
CHECK 24 | Create File Extension. Verify new File Extension can be added. | CreateFileExtension | Julie Bu | Pass
CHECK 25 | Create/Edit Filters for Html, Indesign, JavaProperties, JavaScript, Jsp, MS Office 2010, MS Office Doc, MS Office Excel, MS Office PowerPoint, OpenOffice, Xml | CreateFilters | Julie Bu | Pass
CHECK 26 | Create File Profiles for Word 03, Word 07, Excel 03, Excel 07, PPT 03, PPT 07, MS Office 2010, OpenOffice, HTML, Text, RTF and xml. Verify File Profiles can be created and Edited. | CreateFileProfile | Julie Bu | Pass
CHECK 27 | To create new jobs, upload files Word 03, Word 07, Excel 03, Excel 07, PPT 03, PPT 07, MS Office 2010, OpenOffice, HTML, Text, RTF, FM9, MIF, INDD4, INDD5, INDD 5.5, idml, jsp, java script, java properties, java, rc, resx, passolo, xlf, xlz and xml. Check the job details. Verify the jobs are created correctly | PrepareCreatingJob/Createjob | Julie Bu | Pass
CHECK 28 | Verify RSS reader job can be created successfully. | No testcase now | Julie Bu | Pass
CHECK 29 | Create jobs via Desktop Icon and WebDI.Verify jobs can be created successfully. | Skip | Julie Bu | Pass
CHECK 30 | Verify Add/Delete/Download/Upload job file works correctly. | No testcase now | Julie Bu | Pass
CHECK 31 | Go to Job details page. Dispatch the Ready jobs. Verify the jobs can be dispatched. | MyJobsDetailsDispatch | Julie Bu | Pass
CHECK 32 | Go to Job details page. Verify Details Word Counts can be displayed correctly. | VerifyJobWordCounts | Julie Bu | Pass
CHECK 33 | Go to Job details page. Discard the workflows for the job. Verify workflows can be discarded. | MyJobsDetailsDiscard | Julie Bu | Pass
CHECK 34 | Go to Job details page.Verify jobs can be exported and downloaded. | VerifyJobExport | Julie Bu | Pass
CHECK 35 | Reassign Ready and In Progress jobs. Verify the jobs can be reassigned. | Jester done. | Julie Bu | Pass
CHECK 36 | Skip Activities in the job detail page. Verify the Activities can be skipped. | Jester done. | Julie Bu | Pass
CHECK 37 | Check the Cost Report of localized jobs. Verify the Cost is calculated correctly. | No testcase now | Julie Bu | Pass
CHECK 38 | Check all items under My Jobs are displayed correctly. | MyJobsAllStatusVerify MyJobsReadyVerify | Julie Bu | Pass
CHECK 39 | Check all items under My Activities are displayed correctly. (For PM user) | MyActivitiesAllStatusVerify MyActivitiesAvailableVerify MyActivitiesFinishedVerify | Julie Bu | Pass
CHECK 40 | Check the Reports of localized Jobs. Verify all Reports can be opened/saved in expected format with correct data. | No testcase now | Julie Bu | Pass
CHECK 41 | Create CVS Server, CVS Module configurations and Module mappings, Verify CVS Connector works correctly. | No testcase now | Julie Bu | Pass
User: Local/Super Localization Participant
CHECK 42 | Log in as Translator Users as Localization Particapant. CHECK 42.01 - Verify the information under My Activities Available and In Progress. CHECK 42.02 - Check the Available jobs in My Activities. Verify the jobs can be accepted. | CreateSuperUsers, VerifyActivityStatus VerifyActivityStatusAccept | Julie Bu | Pass
CHECK 43 | Translate the jobs on online Editor. Verify the jobs can be translated. | MyActivityJobEditorVerify | Julie Bu | Pass
CHECK 44 | Translate the jobs offline in xliff & RTF formats.Verify the jobs can be downloaded, translated and uploaded. | No testcase now | Julie Bu | Pass
CHECK 45 | Tanslatione Edit report can be download and uploaded, translated and uploaded inlcuding comment. |  | Julie Bu | Pass
CHECK 46 | Submit the jobs. Verify the job status turns to Finished and can't be edited any longer. | VerifyJobFinished | Julie Bu | Pass
CHECK 47 | Log in as Reviewer Users as Localization Particapant. Check the Available jobs in My Activities. Verify the jobs can be accepted. | VerifyActivityStatusReviewer | Julie Bu | Pass
CHECK 48 | Review the job detail and add comments to the job. Verify the commetns can be added. | ActivityJobCommentReviewer | Julie Bu | Pass
CHECK 49 | Reviewer Comment Report can be downloaded and uploaded with new comment. |  | Julie Bu | Pass
CHECK 50 | Submit the jobs. Verify the job status turns to Finished and can't be edited any longer. | ActivityJobFinishedReviewer | Julie Bu | Pass
Old Jobs
CHECK 51 | Checks 11, from CHECK 30 to 40 and from 42 to 46 should also be tested with jobs created before the GS update. | CreateSuperUsers, VerifyActivityStatus VerifyActivityStatusAccept | Julie Bu | Pass
CHECK 52 | Translation edit report and reviewer comment report which downloaded from old version can be uploaded to new version of GS. | CreateSuperUsers, VerifyActivityStatus VerifyActivityStatusAccept | Julie Bu | Pass